## Slide 1
Licia Florio
AARC All Hands Meeting
Authentication and Authorisation for Research and Collaboration
AARC Overview
21-23 Nov 2017, Amsterdam
AARC Project Coordinator
Presenter affiliation

## Slide 2: What has happened so
AARC objectives and target group
Administrative info
Progresses from last meeting
Engagement with global relevant activities

## Slide 3: AARC Vision
  Avoid a future in which new research collaborations develop independent AAIs
  Deliver production-ready architectural building blocks and best practices to enable r/e-infrastructures to build interoperable AAI

## Slide 4: Who are our main ‘customers’?
Research and e-infrastructures
  AARC should act as the interface between the eScience and the federations/eduGAIN
Libraries?
  Not really in scope for AARC2
  We should continue and promote the work done in the last 2 years.
Everything that involves campus and institutions is not in scope
  Unless it is about providing recommendations

## Slide 5
Administrative info

## Slide 6: Project Overview - Consortium Agreement
AARC2 consortium agreement signed in Sept
Two aspects need clarifying:
  IPR
  Financial bankruptcy of a partner
IPR (background information of the agreement)
  The IPR (“Whatever changes made to the software within the project the IPR remains with Organisation A”) is not in line with general IP law, and in particular not in line with the fundamental IP principle establishing that “Results are owned by the Party that generates them” (Section 8): if a Party makes a fundamental change to the Organisation A software (derivative work), that change is a Result that no longer belongs to Organisation A but to the Party having generated that Result.
  This fundamental IP principle is also established in the Grant Agreement that takes precedence over the Consortium Agreement.

## Slide 7: Project Overview – Consortium Agreement
Financial bankruptcy of a partner
  The EC Guaranteed Fund may not always be used to recover budget given to a partner that defaults
  This results in the consortium having to absorb the costs.
Mitigation of this risk
  AARC2 CA includes the rights for the Coordinator to take the necessary steps to assess partners financial risks.
  Prior to distributing the pre-financing, GÉANT has carried out a financial evaluation of the partners.
  The mitigation in place was to allocate only part of the pre-financing to partners that did not have the highest ranking
  Such a process is in place and GÉANT will continue to carry out periodical checks.

## Slide 8: AARC Project Board
AARC Board appointed:
  Davide Vaghetti (GARR), Tiziana Ferrari (EGI), Klaas Wierenga (GÉANT), Petr Holub (BBMRI-ERIC), Tommi Nyrönen (CSC/Elixir) and Ingemar Häggström (EISCAT)
Meets 3 times per year.
Duties of the board:
  execution of minor budget adjustments;
  supervision of the performance of all the Consortium members in the Project, and the introduction of remedial actions to be taken when the Project is not progressing to plan;
  advice in case of disputes;
  advice the coordinator on changes to the budget and/or any other change to what described in the DoW.

## Slide 9
Progresses

## Slide 10: Make AARC Results available outside AARC

## Slide 11: AEGIS and CEF
r/ e-infras
NA3
SA1
NA1
NA2
JRA1
AEGIS
CEF
FIM4R
Results we want others to use/get
REFEDS
WISE
IGTF
Ensure sustainability of AARC results

## Slide 12: Progresses since kick-off meeting
Started executing engagement plan
Discussing a collaboration agreement with EOSCpilot
Good conversation with other infrastructures via AEGIS
Agreed to look in more detail to the LF AAI requirements and pilot
  Significant progresses on this

## Slide 13: Slower progresses than planned
Pilots – things not yet completely running
  KPI: deliver 3 pilots in the first 10 months of AARC
  LS AAI needs to start asap
Training – good progresses in terms of requirements
  But we need to agree on what to start to implement
Infoshare – we have not had any!

## Slide 14: Resources
Human effort is still a problem
  Some people leave
  Some people are not able to spend as much as planned
  Not easy to find resources with the skills we need
Figures not clear, not everybody has reported time
We need to avoid underspending

## Slide 15
name@yourorg.org